## Task_Table1
Name | Start_Date | Finish_Date
Training Rollout Project | March 1, 2023 9:00 AM | October 17, 2023 6:00 PM
PREPARATION PHASE | March 7, 2023 9:00 AM | March 27, 2023 6:00 PM
Conduct course research | March 7, 2023 9:00 AM | March 9, 2023 6:00 PM
Draft course outline | March 13, 2023 9:00 AM | March 15, 2023 6:00 PM
Send outline to training team for review | March 16, 2023 9:00 AM | March 16, 2023 6:00 PM
Update course outline | March 23, 2023 9:00 AM | March 23, 2023 6:00 PM
Send outline to training manager for review | March 24, 2023 9:00 AM | March 24, 2023 6:00 PM
Outline approved | March 24, 2023 6:00 PM | March 24, 2023 6:00 PM
Finalise course outline | March 27, 2023 9:00 AM | March 27, 2023 6:00 PM
RECORDING PHASE | March 27, 2023 9:00 AM | August 3, 2023 6:00 PM
Write training notes | March 28, 2023 9:00 AM | April 11, 2023 6:00 PM
Record training videos | March 27, 2023 9:00 AM | May 29, 2023 6:00 PM
Edit training videos | May 30, 2023 8:00 AM | June 13, 2023 3:00 PM
Upload to the cloud | July 10, 2023 9:00 AM | July 11, 2023 6:00 PM
Quality control review | July 26, 2023 9:00 AM | August 3, 2023 6:00 PM
Make video ammendments | May 15, 2023 9:00 AM | May 18, 2023 6:00 PM
Training team review | May 19, 2023 9:00 AM | May 29, 2023 6:00 PM
Video content approved | May 29, 2023 6:00 PM | May 29, 2023 6:00 PM
Upload to LMS | June 7, 2023 9:00 AM | June 8, 2023 6:00 PM
DOCUMENTATION PHASE | May 30, 2023 9:00 AM | September 1, 2023 6:00 PM
Write reference guides | May 30, 2023 9:00 AM | June 20, 2023 6:00 PM
Write course questions | August 8, 2023 3:00 PM | August 22, 2023 3:00 PM
Write course description for website | July 12, 2023 9:00 AM | July 25, 2023 6:00 PM
Write exercises | July 12, 2023 9:00 AM | July 25, 2023 6:00 PM
Quality control review | August 28, 2023 9:00 AM | September 1, 2023 6:00 PM
Documentation approved | September 1, 2023 6:00 PM | September 1, 2023 6:00 PM
GO LIVE PHASE | September 5, 2023 9:00 AM | September 6, 2023 6:00 PM
Upload to LMS | September 5, 2023 9:00 AM | September 6, 2023 6:00 PM
Set course live | September 6, 2023 6:00 PM | September 6, 2023 6:00 PM
LIVE TRAINING PHASE | March 1, 2023 9:00 AM | October 17, 2023 6:00 PM
Organise Training Teams | March 1, 2023 9:00 AM | October 4, 2023 6:00 PM
Assign trainers to teams | March 1, 2023 9:00 AM | March 2, 2023 6:00 PM
Assign teams to regions | August 9, 2023 9:00 AM | August 14, 2023 6:00 PM
Travel and Accommodation | September 12, 2023 9:00 AM | October 4, 2023 6:00 PM
Research local hotels | September 15, 2023 9:00 AM | September 26, 2023 6:00 PM
Create hotel shortlist | September 12, 2023 9:00 AM | September 21, 2023 6:00 PM
Send shortlist to training manager | September 12, 2023 9:00 AM | September 12, 2023 6:00 PM
Get budget approval | September 18, 2023 9:00 AM | September 21, 2023 6:00 PM
Book hotel | October 3, 2023 9:00 AM | October 3, 2023 6:00 PM
Hotel booked | October 3, 2023 6:00 PM | October 3, 2023 6:00 PM
Book flights | October 4, 2023 9:00 AM | October 4, 2023 6:00 PM
Flight booked | October 4, 2023 6:00 PM | October 4, 2023 6:00 PM
Venues | August 15, 2023 9:00 AM | August 25, 2023 6:00 PM
Liaise with local contacts re: venues | August 15, 2023 9:00 AM | August 21, 2023 6:00 PM
Create venue shortlist | August 22, 2023 9:00 AM | August 22, 2023 6:00 PM
Send shortlist to training manager | August 22, 2023 9:00 AM | August 22, 2023 6:00 PM
Get budget approval | August 23, 2023 9:00 AM | August 25, 2023 6:00 PM
Book venue | August 25, 2023 9:00 AM | August 25, 2023 6:00 PM
Organise equipment | August 21, 2023 9:00 AM | August 25, 2023 6:00 PM
Source laptops for all trainers | August 21, 2023 9:00 AM | August 25, 2023 6:00 PM
Obtain laptop specifications | August 21, 2023 9:00 AM | August 21, 2023 6:00 PM
Travel and Accommodation | August 28, 2023 9:00 AM | September 29, 2023 6:00 PM
Research local hotels | August 28, 2023 9:00 AM | September 29, 2023 6:00 PM
Create hotel shortlist | September 1, 2023 9:00 AM | September 8, 2023 6:00 PM
Send shortlist to training manager | September 1, 2023 9:00 AM | September 1, 2023 6:00 PM
Get budget approval | September 5, 2023 9:00 AM | September 8, 2023 6:00 PM
Book hotel | September 11, 2023 9:00 AM | September 11, 2023 6:00 PM
Hotel booked | September 11, 2023 6:00 PM | September 11, 2023 6:00 PM
Book flights | September 25, 2023 9:00 AM | September 25, 2023 6:00 PM
Flight booked | September 25, 2023 6:00 PM | September 25, 2023 6:00 PM
Expenses | September 22, 2023 9:00 AM | October 17, 2023 6:00 PM
Approve budget | October 5, 2023 9:00 AM | October 6, 2023 6:00 PM
Organise company credit card | October 9, 2023 9:00 AM | October 17, 2023 6:00 PM
Print out expense forms | September 22, 2023 9:00 AM | September 22, 2023 6:00 PM