## New_Biz_Plan
Milestone | Task_Mode | Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names | Percent_Work_Complete
| Auto Scheduled | New Business | [5 empty] | 0%
| Auto Scheduled | Phase 1 - Strategic Plan | [5 empty] | 0%
| Auto Scheduled | Self-Assessment | 3 days | 2024-11-07 | 2024-11-09 |  |  | 0%
| Auto Scheduled | Define business vision | 1 day | 2024-11-07 | 2024-11-07 | 3 | Manager | 0%
| Auto Scheduled | Identify available skills, information and support | 1 day | 2024-11-08 | 2024-11-08 | 4 | Business Advisor,Manager | 0%
| Auto Scheduled | Decide whether to proceed | 1 day | 2024-11-09 | 2024-11-09 | 5 | Manager | 0%
| Auto Scheduled | Define the Opportunity | [5 empty] | 0%
| Auto Scheduled | Research the market and competition | 1 day | 2024-11-10 | 2024-11-10 | 6 | Business Advisor | 0%
| Auto Scheduled | Interview owners of similar businesses | 5 days | 2024-11-11 | 2024-11-17 | 7 | Owners | 0%
| Manually Scheduled | Identify needed resources | 2 days | 2024-11-18 | 2024-11-21 | 8 | Business Advisor,Peers | 0%
| Manually Scheduled | Identify operating cost elements | 2 days | 2024-11-22 | 2024-11-23 | 9 | Accountant | 0%
| Auto Scheduled | Evaluate Business Approach | [5 empty] | 0%
| Auto Scheduled | 1 | 1 day | 2024-11-24 | 2024-11-24 | 10 | Manager | 0%
| Auto Scheduled | Identify on-going business purchase opportunities | 1 day | 2024-11-25 | 2024-11-25 | 12 | Manager | 0%
| Auto Scheduled | Research franchise possibilities | 1 day | 2024-11-28 | 2024-11-28 | 13 | Manager | 0%
| Auto Scheduled | Summarize business approach | 1 day | 2024-11-29 | 2024-11-29 | 14 | Manager | 0%
| Auto Scheduled | Evaluate Potential Risks and Rewards | [5 empty] | 0%
| Auto Scheduled | Assess market size and stability | 2 days | 2024-11-25 | 2024-11-28 | 12 | Business Advisor | 0%
| Auto Scheduled | Estimate the competition | 1 day | 2024-11-29 | 2024-11-29 | 17 | Business Advisor | 0%
| Auto Scheduled | Assess needed resource availability | 2 days | 2024-11-30 | 2024-12-01 | 18 | Business Advisor | 0%
| Auto Scheduled | Evaluate realistic initial market share | 1 day | 2024-12-02 | 2024-12-02 | 19 | Business Advisor | 0%
| Auto Scheduled | Determine financial requirements | 2 days | 2024-11-30 | 2024-12-01 | 15 | Business Advisor | 0%
| Auto Scheduled | Review personal suitability | 1 day | 2024-12-02 | 2024-12-02 | 21 | Manager | 0%
| Auto Scheduled | Evaluate initial profitability | 1 day | 2024-12-05 | 2024-12-05 | 22 | Manager | 0%
| Auto Scheduled | Review and modify the strategic plan | 2 days | 2024-12-06 | 2024-12-07 | 23 |  | 0%
Milestone | Auto Scheduled | Confirm decision to proceed | 0 days | 2024-12-07 | 2024-12-07 | 24 |  | 0%
| Auto Scheduled | Phase 2 - Define the Business Opportunity | [5 empty] | 0%
| Auto Scheduled | Define the Market | [5 empty] | 0%
| Auto Scheduled | Access available information | 1 day | 2024-12-08 | 2024-12-08 | 25 | Business Advisor | 0%
| Auto Scheduled | Create market analysis plan | 2 days | 2024-12-09 | 2024-12-12 | 28 | Business Advisor | 0%
| Auto Scheduled | Implement market analysis plan | 5 days | 2024-12-13 | 2024-12-19 | 29 | Business Advisor | 0%
| Auto Scheduled | Identify competition | 2 days | 2024-12-20 | 2024-12-21 | 30 | Business Advisor | 0%
| Auto Scheduled | Summarize the market | 2 days | 2024-12-22 | 2024-12-23 | 31 | Business Advisor | 0%
| Auto Scheduled | Identify target market niche | 1 day | 2024-12-26 | 2024-12-26 | 32 | Business Advisor | 0%
| Auto Scheduled | Identify Needed Materials and Supplies | [5 empty] | 0%
| Auto Scheduled | Select a business approach (from "Evaluate Business Approach" above) | 2 days | 2024-12-27 | 2024-12-28 | 28SS,33 | Manager | 0%
| Auto Scheduled | Identify management staff resources | 1 day | 2024-12-29 | 2024-12-29 | 35 | Manager | 0%
| Auto Scheduled | Identify staffing requirements | 1 day | 2024-12-30 | 2024-12-30 | 36 | Manager | 0%
| Auto Scheduled | Identify needed raw materials | 1 day | 2025-01-02 | 2025-01-02 | 37 | Manager | 0%
| Auto Scheduled | Identify needed utilities | 1 day | 2025-01-03 | 2025-01-03 | 38 | Manager | 0%
| Auto Scheduled | Summarize operating expenses and financial projections | 1 day | 2025-01-04 | 2025-01-04 | 39 | Manager | 0%
| Auto Scheduled | Evaluate Potential Risks and Rewards | [5 empty] | 0%
| Auto Scheduled | Assess market size and stability | 2 days | 2025-01-05 | 2025-01-06 | 40 | Manager | 0%
| Auto Scheduled | Assess needed resources availability | 2 days | 2025-01-09 | 2025-01-10 | 42 | Manager | 0%
| Auto Scheduled | Forecast financial returns | 2 days | 2025-01-11 | 2023-01-12 | 43 | Accountant | 0%
| Auto Scheduled | Review and modify the business opportunity | 1 day | 2025-01-13 | 2023-01-13 | 44 |  | 0%
Milestone | Auto Scheduled | Confirm decision to proceed | 0 days | 2025-01-13 | 2023-01-13 | 45 | Business Advisor,Peers,Lawyer,Accountant | 0%
| Auto Scheduled | Phase 3 - Plan for Action | [5 empty] | 0%
| Auto Scheduled | Develop Detailed 5-Year Business Plan | [5 empty] | 0%
| Auto Scheduled | Describe the vision and opportunity | 1 day | 2025-01-16 | 2023-01-16 | 46 | Business Advisor | 0%
| Auto Scheduled | List assumptions | 1 day | 2025-01-17 | 2023-01-17 | 49 | Business Advisor | 0%
| Auto Scheduled | Describe the market | 1 day | 2025-01-18 | 2023-01-18 | 50 | Business Advisor | 0%
| Auto Scheduled | Describe the new business | 1 day | 2025-01-19 | 2023-01-19 | 51 | Business Advisor | 0%
| Auto Scheduled | Describe strengths, weaknesses, assets and threats | 1 day | 2025-01-20 | 2023-01-20 | 52 | Business Advisor | 0%
| Auto Scheduled | Estimate sales volume during startup period | 1 day | 2025-01-23 | 2023-01-23 | 53 | Business Advisor,Accountant | 0%
| Auto Scheduled | Forecast operating costs | 1 day | 2025-01-24 | 2023-01-24 | 54 | Business Advisor,Accountant | 0%
| Auto Scheduled | Establish pricing strategy | 1 day | 2025-01-25 | 2023-01-25 | 55 | Business Advisor | 0%
| Auto Scheduled | Forecast revenue | 1 day | 2025-01-26 | 2023-01-26 | 56 | Business Advisor | 0%
| Auto Scheduled | Summarize pro-forma financial statement | 2 days | 2025-01-27 | 2023-01-30 | 57 | Business Advisor | 0%
| Auto Scheduled | Develop break-even analysis | 1 day | 2025-01-31 | 2023-01-31 | 58 | Business Advisor | 0%
| Auto Scheduled | Develop cash-flow projection | 1 day | 2025-02-01 | 2023-02-01 | 59 | Business Advisor | 0%
| Auto Scheduled | Identify licensing and permitting requirements | 1 day | 2025-02-02 | 2023-02-02 | 60 | Business Advisor | 0%
| Auto Scheduled | Develop startup plan | 2 days | 2025-02-03 | 2023-02-06 | 61 | Business Advisor | 0%
| Auto Scheduled | Develop sales and marketing strategy | 1 day | 2025-02-07 | 2023-02-07 | 62 | Business Advisor | 0%
| Auto Scheduled | Develop distribution structure | 1 day | 2025-02-08 | 2023-02-08 | 63 | Business Advisor | 0%
| Auto Scheduled | Describe risks and opportunities | 2 days | 2025-02-09 | 2025-02-10 | 64 | Business Advisor | 0%
| Auto Scheduled | Publish the business plan | 1 day | 2025-02-13 | 2025-02-13 | 65 | Business Advisor | 0%
Milestone | Auto Scheduled | Confirm decision to proceed | 0 days | 2025-02-13 | 2025-02-13 | 66 | Business Advisor | 0%
| Auto Scheduled | Phase 4 - Proceed With Startup Plan | [5 empty] | 0%
| Auto Scheduled | Choose a location | 1 day | 2025-02-14 | 2025-02-14 | 67 |  | 0%
| Auto Scheduled | Establish Business Structure | [5 empty] | 0%
| Auto Scheduled | Choose a Name | [5 empty] | 0%
| Auto Scheduled | Identify implications | 1 day | 2025-02-15 | 2025-02-15 | 69 | Lawyer | 0%
| Auto Scheduled | Research name availability | 1 day | 2025-02-16 | 2025-02-16 | 72 | Lawyer | 0%
| Auto Scheduled | Choose a Bank | [5 empty] | 0%
| Auto Scheduled | Establish accounts | 4 days | 2025-02-17 | 2025-02-22 | 73 | Banker | 0%
| Auto Scheduled | Establish line of credit | 1 day | 2025-02-23 | 2025-02-23 | 75 | Banker | 0%
| Auto Scheduled | Choose legal representation | 1 day | 2025-02-24 | 2025-02-24 | 75SS,76 | Lawyer | 0%
| Auto Scheduled | Select business tax-basis category | 2 days | 2025-02-27 | 2025-02-28 | 77 | Lawyer,Accountant | 0%
| Auto Scheduled | Choose capital funding source | 2 days | 2025-03-01 | 2025-03-02 | 78 | Manager | 0%
Milestone | Auto Scheduled | Commit capital funding | 0 days | 2025-03-02 | 2025-03-02 | 79 | Manager | 0%
| Auto Scheduled | Establish the Operating Control Base | [5 empty] | 0%
| Auto Scheduled | Choose and set up the accounting system | 2 days | 2025-03-03 | 2025-03-06 | 79,80 | Accountant | 0%
| Auto Scheduled | Obtain required licenses and permits | 4 days | 2025-03-07 | 2025-03-10 | 82 | Lawyer,Government Agency | 0%
| Auto Scheduled | Obtain needed insurance | 4 days | 2025-03-13 | 2025-03-16 | 83 | Accountant | 0%
| Auto Scheduled | Establish security plan | 2 days | 2025-03-17 | 2025-03-20 | 84 | Business Advisor,Lawyer | 0%
| Auto Scheduled | Develop Marketing Program | [5 empty] | 0%
| Auto Scheduled | Establish an advertising program | 2 days | 2025-02-16 | 2025-02-17 | 73SS | Business Advisor | 0%
| Auto Scheduled | Develop a logo | 1 day | 2025-02-20 | 2025-02-20 | 87 | Business Advisor,Lawyer | 0%
| Auto Scheduled | Order promotional materials | 1 day | 2025-02-21 | 2025-02-21 | 88 | Business Advisor | 0%
| Auto Scheduled | Provide Physical Facilities | [5 empty] | 0%
| Auto Scheduled | Secure operation space | 5 days | 2025-03-21 | 2025-03-27 | 85,89 | Lawyer | 0%
| Auto Scheduled | Select computer network hardware | 1 day | 2025-03-28 | 2025-03-28 | 91 | Information Services | 0%
| Auto Scheduled | Select computer software | 1 day | 2025-03-29 | 2025-03-29 | 92 | Information Services | 0%
| Auto Scheduled | Establish utilities | 3 days | 2025-03-30 | 2025-04-03 | 93 | Manager | 0%
| Auto Scheduled | Provide furniture and equipment | 4 days | 2025-04-04 | 2025-04-07 | 94 | Manager | 0%
| Auto Scheduled | Move in | 1 day | 2025-04-10 | 2025-04-10 | 95 | Manager | 0%
| Auto Scheduled | Provide Staffing | [5 empty] | 0%
| Auto Scheduled | Interview and test candidates | 14 days | 2025-03-03 | 2025-03-22 | 79 | Manager | 0%
| Auto Scheduled | Hire staff | 10 days | 2025-03-23 | 2025-04-05 | 98 | Manager | 0%
| Auto Scheduled | Train staff | 16 days | 2025-04-06 | 2025-04-27 | 99 | Manager | 0%
Milestone | Auto Scheduled | Start up the business | 0 days | 2025-04-27 | 2025-04-27 | 96,100 | Manager | 0%

## Resource_Table1
ID | Resource_Name | Type | Initials | Max_Units | Std_Rate | Ovt_Rate | Cost_Use | Accrue_At | Base_Calendar
1 | Business Advisor | Work | B | 100% | $100.00/h | $200.00/h | 0 | Prorated | Standard
2 | Peers | Work | P | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
3 | Lawyer | Work | L | 100% | $300.00/h | $500/h | 0 | Prorated | Standard
4 | Government Agency | Work | G | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
5 | Manager | Work | M | 100% | $50.00/h | $100.00/h | 0 | Prorated | Standard
6 | Owners | Work | O | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
7 | Accountant | Work | A | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
8 | Banker | Work | B | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
9 | Information Services | Work | I | 100% | $0.00/h | $0.00/h | 0 | Prorated | Standard
10 | Business Permit | Cost | BP |  |  |  |  | Prorated | Standard